GEOPOLITICAL SHOCKS AND DEFENSE EQUITY RETURNS

A Neural Event Study

Condensed 2–3 Week Roadmap  |  3-Person Team

# 1. What This Project Is

This project studies how geopolitical events (wars, sanctions, arms deals, defense budget decisions) affect the stock prices of US defense companies. It uses a neural network instead of classical OLS to capture non-linear patterns that linear methods miss.

The core methodology is an event study: for each geopolitical incident, compute the Cumulative Abnormal Return (CAR) — the portion of stock movement attributable to the event rather than market-wide moves. A neural network then predicts CARs using event text embeddings (NLP) and macro variables. SHAP values decompose each prediction into feature contributions, producing the core analytical finding.

# 2. Scope Decisions for the Sprint

To hit a 2–3 week timeline, the following simplifications apply:

- Use MLP only. Skip the Transformer unless you have 500+ events AND multiple concurrent events need joint modeling — this is unlikely and the complexity is not worth it.

- EDA is functional, not exhaustive. Produce the key plots (CAR distributions, box plots by CAMEO and ticker, macro scatter plots). Do not over-iterate.

- Paper is a working paper, not a submission. Target 15–18 pages. Cut the Literature Review to 1 page of citations and move on.

- Walk-forward CV uses 3–4 folds max. Enough to show temporal honesty without consuming a week on evaluation alone.

# 3. Timeline

| Week | Phase | Who | Tasks |
| --- | --- | --- | --- |
| Week 1 | Data Pipeline & Setup | A | Fetch prices (yfinance), GDELT events (BigQuery), FRED macro data. Compute CARs (OLS). Assemble modeling dataset. |
| Week 1 |  | B | Set up repo, environment, PyTorch. Write walk-forward CV splitter. Build sentence embedding pipeline (all-MiniLM-L6-v2). |
| Week 1 |  | C | Read event study methodology. Manual SIPRI/DSCA arms-deal dataset. Count events per CAMEO category — confirm MLP is sufficient. |
| Week 2 | EDA + Model Build | A | Data quality checks. Sanity check: Russia-Ukraine Feb 2022 CARs positive for LMT/NOC? Fix pipeline bugs. |
| Week 2 |  | B | EDA: CAR distributions, box plots by ticker/CAMEO, macro correlations. OLS baseline R². Build & train MLP (389→256→128→64→1). Tune with walk-forward CV. Compute SHAP values. |
| Week 2 |  | C | Visualizations: CAR plots, SHAP bar charts, SHAP waterfall plots for 3–5 notable events. Draft EDA section. |
| Week 3 | Ablation, SHAP & Write-Up | A | Write Data section. Run ablation logging (embedding-only, macro-only, full). Freeze final dataset. |
| Week 3 |  | B | Ablation studies. Finalize model. Clean and document all code. |
| Week 3 |  | C | Interpret SHAP results jointly. Write full paper (Introduction, Literature, Results, Discussion, Conclusion). Assemble final draft. |

# 4. Weekly Deliverable Checkpoints

| Checkpoint | Deliverables |
| --- | --- |
| Week 1 end | Price CSV, GDELT events CSV, macro CSV, CARs CSV, modeling dataset assembled, repo live with all pipeline scripts |
| Week 2 end | OLS baseline R² recorded, MLP trained with walk-forward CV metrics, SHAP values computed, all EDA plots generated |
| Week 3 end | Ablation results, finalized model, complete paper draft, clean documented codebase |

# 5. Model Specification (MLP)

## Architecture

- Input: 384-dim event embedding (all-MiniLM-L6-v2) + 5 macro features (VIX, 10Y yield, HY spread, USD index, WTI crude) = 389 dimensions

- Hidden layers: 256 → 128 → 64, ReLU activations, dropout 0.2 between layers

- Output: 1 scalar (predicted CAR)

- Loss: MSE (switch to Huber loss δ=1.0 if CAR outliers are severe)

- Optimizer: AdamW, lr=1e-3, weight_decay=1e-4

## Training Protocol

- Walk-forward cross-validation: train on years T, test on T+1 and T+2. Repeat rolling forward. Use 3–4 folds.

- Report out-of-sample R² and MAE. Compare against OLS baseline (CAR ~ macro dummies).

- Ablation: (1) embedding only, (2) macro only, (3) full model. Record R² for each.

# 6. SHAP Analysis

SHAP is the core intellectual contribution. Run it after the model is finalized.

- Use shap.KernelExplainer or shap.DeepExplainer depending on model complexity.

- Produce: (1) mean absolute SHAP by macro feature — which macro variable matters most; (2) mean absolute SHAP by CAMEO category — which event types drive signal; (3) SHAP by ticker — do PLTR/KTOS differ from LMT/NOC; (4) waterfall plots for 3–5 notable events (Russia-Ukraine invasion, a major arms deal, a sanctions announcement).

- Interpretation session (all three, ~2 hours): Does VIX dominate? (macro trade, not event trade.) Do conflict events (19x) beat threats (13x)? (markets surprised by escalation.) Do non-traditional contractors respond differently?)

# 7. Paper Structure (15–18 pages)

- Introduction (1–2 pages): Motivation, research question, preview of findings.

- Literature Review (1 page): 8–10 key citations. Skim, don't deep-dive.

- Data (2–3 pages): Sources, filtering rules, summary stats, 2–3 EDA figures. Person A writes.

- Methodology (2–3 pages): Event study setup, MLP architecture, walk-forward CV, SHAP. Person B writes.

- Results (3–4 pages): Out-of-sample performance, ablation table, SHAP figures. Person C writes.

- Discussion (1–2 pages): Economic interpretation, limitations.

- Conclusion (0.5 page): Summary and future work.

# 8. Risks and Mitigations

| Risk | Mitigation |
| --- | --- |
| Noisy GDELT events | NumMentions ≥ 5; deduplicate by (date, actor1, actor2, eventcode); spot-check 50 events manually |
| Small per-category sample | Count events in Week 1. If < 50 per category, collapse CAMEO codes. MLP is sufficient — skip Transformer. |
| Overlapping event windows | Drop events within 10 days of another event for the same ticker. Document count. |
| PLTR / KTOS short history | Report results separately for pre-2020 and post-2020 tickers. |
| Overfitting | Walk-forward CV, dropout (0.2), AdamW weight decay. Monitor train vs test loss each epoch. |

# 9. Start Today

- Create the GitHub repo with folder structure: data/raw/, data/processed/, models/, notebooks/, paper/.

- Get a FRED API key at fred.stlouisfed.org (2 minutes, free).

- Set up Google BigQuery free tier — GDELT is pre-loaded and you get 1 TB free queries/month.

- Install the environment: yfinance, pandas, numpy, scipy, fredapi, sentence-transformers, torch, shap, statsmodels, matplotlib, seaborn.

Build something worth reading.